## Lists
Status | Criticality | Readiness | Wave | Decision | Transport
Not Started | Low | Not Ready | Wave 0 - Pilot | GO | MPLS
In Progress | Medium | Partially Ready | Wave 1 - Low Risk | CONDITIONAL GO | DIA
Blocked | High | Ready | Wave 2 - Standard | NO-GO | Broadband
Complete | Critical | N/A | Wave 3 - Complex |  | Fiber
N/A |  |  | Wave 4 - Critical |  | 4G/5G
|  |  | Hold |  | Internet
Other

## WAN Inventory
1. Current WAN Inventory
Capture every site, carrier and WAN service before designing the migration.
Site ID | Site / Location | Business Criticality | Primary Transport | Secondary Transport | Provider(s) | Bandwidth | Contract End | Current SLA / Notes | Migration Owner | Status

## Application Matrix
2. Application Dependency Matrix
Map critical applications to users, sites, destinations, performance needs and security requirements.
Application | Business Owner | Sites / Users | Destination | Criticality | Latency Need | Jitter Need | Loss Tolerance | Security / Segmentation | Preferred Path | Backup Path | Test Owner | Status

## Performance Baseline
3. Performance Baseline
Measure the current WAN before changing it so post-migration results can be compared objectively.
Site / App | Metric | Current Baseline | Target / Acceptance | Measurement Method | Sample Period | Owner | Status | Notes
Example: HQ - Voice | Latency | 35 ms | <= 50 ms | Monitoring platform | 7 days | Network | Not Started | Replace example with your own data
Example: HQ - Voice | Jitter | 8 ms | <= 20 ms | Monitoring platform | 7 days | Network | Not Started
Example: Branch 12 - SaaS | Packet Loss | 0.3% | < 1% | Synthetic test | 7 days | Network | Not Started

## Target Design
4. Target Hybrid WAN Design
Define target underlays, overlay behavior, path policy, segmentation and MPLS retention by site profile.
Site / Profile | Primary Underlay | Secondary Underlay | Tertiary / Backup | SD-WAN Role | Routing / Segmentation | Internet Breakout | Key App Policies | MPLS Decision | Design Owner | Status

## Security Readiness
5. Security Readiness
Validate security architecture before enabling local internet breakout or changing traffic paths.
Control Area | Readiness Question | Readiness | Owner | Notes / Evidence
Internet egress architecture | Where will branch internet traffic exit after migration? | Not Ready
Firewall / NGFW policy | Are required policies approved and tested? | Not Ready
DNS / web security | Are branch or cloud-delivered controls ready? | Not Ready
Segmentation | Are VRFs / segments and policy boundaries preserved? | Not Ready
Identity / Zero Trust | Are identity-aware controls required and designed? | Not Ready
SASE integration | Is SASE in scope, future scope, or not required? | Not Ready
Logging / SIEM | Will new branch and SD-WAN events be visible centrally? | Not Ready
Incident response | Are escalation and response paths updated? | Not Ready

## Pilot Checklist
6. SD-WAN Pilot Checklist
Treat the pilot as a rehearsal for production migration, not just a connectivity test.
Check | Acceptance Criteria | Status | Owner | Evidence / Notes
Pilot site selection | Representative mix of site types selected | Not Started
Underlay readiness | All pilot circuits active and tested | Not Started
Overlay connectivity | SD-WAN control / overlay established | Not Started
Routing | Expected routes and redistribution validated | Not Started
Segmentation | Segments / VRFs preserved | Not Started
Application steering | Critical application policies validated | Not Started
QoS | Voice/video classification and priority validated | Not Started
SaaS / cloud | Cloud and SaaS paths validated | Not Started
Internet breakout | Direct internet behavior validated where applicable | Not Started
Security | Security controls and logging validated | Not Started
Failover | Primary / backup transport failover tested | Not Started
Operations | Monitoring and support runbook validated | Not Started
Exit criteria | All critical defects closed or accepted | Not Started

## Migration Waves
7. Migration Wave Planner
Group sites by risk, complexity and dependency rather than only by geography or volume.
Site / Group | Wave | Risk Level | Planned Date | Change Window | Dependencies | Business Contact | Technical Lead | Rollback Owner | Status

## Pre-Cutover
8. Pre-Cutover Checklist
Do not start the change window until critical prerequisites and the rollback path are ready.
Check | Acceptance Criteria | Status | Owner | Evidence / Notes
Change window approved | Formal change / CAB approval confirmed | Not Started
Site contact confirmed | Local business / site contact available | Not Started
Underlays operational | All required WAN circuits tested | Not Started
WAN edge ready | Hardware / virtual edge installed and reachable | Not Started
Configuration reviewed | Peer review completed | Not Started
Routing verified | Routing / redistribution changes reviewed | Not Started
Security rules ready | Required security changes approved | Not Started
Monitoring ready | Telemetry, alarms and dashboards prepared | Not Started
Baseline captured | Current performance baseline recorded | Not Started
Application tests ready | Critical app validation script available | Not Started
Provider contacts ready | Escalation path confirmed | Not Started
Rollback verified | Backout procedure reviewed and executable | Not Started

## Cutover
9. Cutover Checklist
Execute the production change in a controlled, observable sequence.
Step | Acceptance Criteria | Status | Owner | Evidence / Notes
Final GO decision | Migration lead confirms GO | Not Started
Record starting state | Capture routing, alarms and interfaces before change | Not Started
Activate SD-WAN edge | Bring edge into service | Not Started
Verify underlays | Confirm all underlays are reachable | Not Started
Verify overlay | Confirm control connections / tunnels | Not Started
Verify routes | Confirm expected prefixes and path preference | Not Started
Apply traffic policy | Activate app steering / QoS / segmentation | Not Started
Apply security policy | Activate required breakout and security controls | Not Started
Validate traffic paths | Confirm expected primary / backup behavior | Not Started
Monitor alarms | Watch telemetry, logs and incidents | Not Started

## Rollback
10. Rollback Plan
Define objective rollback triggers, authority and recovery steps before cutover begins.
Trigger / Control | Definition | Readiness | Owner | Action / Evidence
Critical application unavailable | Service cannot be restored within agreed window | Not Ready
Routing instability | Persistent or widespread unexpected routing behavior | Not Ready
Security control failure | Required policy / segmentation not enforced | Not Ready
Severe performance degradation | Service below agreed acceptance threshold | Not Ready
Monitoring loss | Operations cannot safely observe the site | Not Ready
Time threshold reached | Insufficient change window remains for safe completion | Not Ready
Rollback authorization | Named authority available to approve rollback | Not Ready
Restore procedure | Legacy routing / config restoration steps documented | Not Ready
Business validation | Method to confirm restored service defined | Not Ready

## Post-Cutover
11. Post-Cutover Validation
A successful cutover is not complete until applications, resilience, security and operations are validated.
Validation Area | Acceptance Criteria | Status | Owner | Evidence / Notes
LAN / WAN reachability | Core site and WAN reachability verified | Not Started
DNS | Name resolution verified | Not Started
Critical applications | Business-critical apps tested | Not Started
SaaS / cloud | Approved SaaS and cloud apps tested | Not Started
Voice / video | Real-time collaboration quality validated | Not Started
Internet access | Internet breakout behavior confirmed | Not Started
Routing | Prefixes, preference and redistribution validated | Not Started
QoS / steering | Traffic classes and app paths validated | Not Started
Failover | Primary / backup transport failover tested | Not Started
Security | Security controls and segmentation validated | Not Started
Logging / monitoring | Events visible to operations and security | Not Started
Operational handover | Runbook, ownership and escalation accepted | Not Started

## MPLS Retirement
12. MPLS Retirement Decision
Retire MPLS only when the new architecture is stable, resilient, supportable and commercially sensible.
Decision Criterion | Acceptance Criteria | Readiness | Owner | Evidence / Notes
Stability period complete | Site has operated stably for the agreed period | Not Ready
Critical apps validated | Application performance accepted over time | Not Ready
Failover proven | Alternative transport resilience validated | Not Ready
Operations ready | Support team accepts steady-state ownership | Not Ready
Security stable | No unresolved security architecture gaps | Not Ready
Underlay diversity adequate | Alternative transports provide sufficient resilience | Not Ready
Commercial terms reviewed | Termination dates / penalties understood | Not Ready
Business approval | Business owner accepts MPLS retirement | Not Ready

## Readiness Gate
13. Final SD-WAN Cutover Readiness Gate
Score eight readiness dimensions before authorizing a production migration wave.
Readiness Area | Question | Assessment | Score | Owner | Evidence | Critical Blocker? | Comments
Architecture | Is the target design approved and understood? | Not Ready | 0 |  |  | No
Connectivity | Are all required underlays installed and validated? | Not Ready | 0 |  |  | No
Applications | Are critical dependencies and tests documented? | Not Ready | 0 |  |  | No
Routing | Is legacy / SD-WAN interworking understood? | Not Ready | 0 |  |  | No
Security | Are required controls and policies ready? | Not Ready | 0 |  |  | No
Pilot | Has the architecture been validated on representative sites? | Not Ready | 0 |  |  | No
Rollback | Is the recovery path documented and executable? | Not Ready | 0 |  |  | No
Operations | Can operations monitor, troubleshoot and support the service? | Not Ready | 0 |  |  | No
READINESS SUMMARY
Total Score | 0
Maximum Score | 16
Critical Blockers | 0
Decision | NO-GO

## Dashboard
Free SD-WAN Migration Checklist & Cutover Planner
Practical workbook for planning an MPLS-to-hybrid-WAN migration from discovery through cutover, validation and MPLS retirement.
Current WAN Inventory + dependencies |  | Pilot Validate assumptions |  | Cutover Execute safely |  | Readiness Gate Decision gate
Workbook Section | Purpose | Complete | In Progress | Blocked | Not Started | N/A | Completion %
WAN Inventory | Sites, circuits, carriers, contracts | 0 | 0 | 0 | 0 | 0 | 0%
Application Matrix | Critical application dependencies | 0 | 0 | 0 | 0 | 0 | 0%
Performance Baseline | Measure current service | 0 | 0 | 0 | 3 | 0 | 0%
Target Design | Target underlays, overlay and policies | 0 | 0 | 0 | 0 | 0 | 0%
Security Readiness | Security before breakout | 0 | 0 | 8 | 0 | 0 | 0%
Pilot Checklist | Representative pilot and exit criteria | 0 | 0 | 0 | 13 | 0 | 0%
Migration Waves | Group sites by risk / complexity | 0 | 0 | 0 | 0 | 0 | 0%
Pre-Cutover | Confirm prerequisites | 0 | 0 | 0 | 12 | 0 | 0%
Cutover | Execute production change | 0 | 0 | 0 | 10 | 0 | 0%
Rollback | Triggers, authority and recovery | 0 | 0 | 9 | 0 | 0 | 0%
Post-Cutover | Validate service and operations | 0 | 0 | 0 | 12 | 0 | 0%
MPLS Retirement | Decide what MPLS can be retired | 0 | 0 | 8 | 0 | 0 | 0%
Final Readiness Decision
NO-GO
How to use this workbook
1. Start with WAN Inventory and Application Matrix.
2. Capture a performance baseline before changing the network.
3. Define target hybrid WAN and security readiness.
4. Run a representative pilot and document exit criteria.
5. Group sites into migration waves based on risk and complexity.
6. Use Pre-Cutover, Cutover and Rollback sheets for each change.
7. Complete Post-Cutover validation before considering MPLS retirement.
8. Use the Readiness Gate before each production wave.
TechTeamSynergy.com - Free planning aid. Adapt thresholds, controls and approvals to your own network, security and change-management environment.