## Blank RACI
TechTeamSynergy — RACI Matrix Template
How to use: enter one project activity per row, then assign R, A, C, I or R/A to each role. The Validation column checks for missing/duplicate accountability, missing responsibility, and excessive consultation.
Activity / Deliverable | Sponsor | Project Manager | Technical Lead | Business Owner | Security | Operations | Validation
Activity 1 | [6 empty] | No Accountable
Activity 2 | [6 empty] | No Accountable
Activity 3 | [6 empty] | No Accountable
Legend: R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed ¦ R/A = same role executes and owns the outcome

## IT Project Example
RACI Example — IT Infrastructure Upgrade
Illustrative example: adapt role names and assignments to your governance model. One clear Accountable owner is shown for each major activity.
Activity | Executive Sponsor | Project Manager | Infrastructure Lead | Security Lead | Operations Lead | Vendor
Approve project scope | A | R | C | C | C | I
Develop technical design | I | A | R | C | C | C
Procure infrastructure | I | A | R | C | C | C
Complete security review | I | C | C | R/A | C | I
Perform implementation | I | A | R | C | C | R
Validate solution | I | A | R | C | R | C
Approve operational handover | I | R | C | C | A | I
Key lesson: technical execution, security acceptance, delivery coordination and operational acceptance are different forms of ownership.

## Network Migration Example
RACI Example — SD-WAN / Network Migration
Illustrative enterprise network migration example. Internal accountability remains explicit even where a service provider performs major delivery tasks.
Activity | Project Manager | Network Architect | Network Operations | Security | Site / Business | Service Provider
Network discovery | A | R | R | C | C | C
Target architecture | C | R/A | C | C | I | C
Security design review | C | R | C | A | I | C
Pilot preparation | A | R | R | C | C | R
Site readiness | A | C | C | I | R | C
Execute migration | A | C | R | I | I | R
Validate service | A | C | R | C | R | C
Operational handover | R | C | A | C | I | C
Key lesson: outsourcing execution does not automatically transfer business or operational accountability to the provider.

## Validation Checklist
RACI Validation Checklist
Live check | Value
Filled activities | 3
Rows OK | 0
No Accountable | 3
Multiple Accountable | 0
No Responsible | 0
Too many Consulted | 0
Check | Question | Good practice | Warning sign
Row check | Does each major activity have one clear Accountable role? | One A per major outcome | No A or multiple As
Row check | Is at least one role Responsible for doing the work? | At least one R | Nobody owns execution
Row check | Are Consulted roles genuinely needed? | Keep C selective | Everyone is C
Row check | Are Informed roles included only when visibility is useful? | Use I for visibility | I becomes a meeting list
Column check | Is one role Accountable for almost everything? | Authority should be distributed realistically | PM or sponsor owns all rows
Column check | Is one role Responsible for almost everything? | Execution should match actual team structure | One overloaded role
Authority check | Does the Accountable role have the authority to approve/accept the outcome? | Accountability follows authority | A cannot make the decision
Governance check | Does the matrix reflect contracts, regulations and real decision rights? | Reality overrides the template | Template conflicts with governance
Review check | Has the matrix been validated with stakeholders? | Agree ownership together | RACI imposed without discussion